## Mirror
Item | Task | Responsible Person | Not Started | In Progress | Complete | Completed by date | Note
Mirror software | Mirror communication with checksum | Thibaud |  |  |  | 2017-05-10
| Measure feedback voltages from HV | Thibaud |  |  |  | 2017-05-10
| Use temperature sensors (+ calibrate them) | Thibaud, Ashish (Serena?) |  |  |  | 2017-05-17
| Picomotor initializing | Thibaud |  |  |  | 2017-06-07 | Need flight encoders
| Software layer and flight operations modes | Yuchen

## Camera
Item | Task | Responsible Person | Not Started | In Progress | Complete | Completed by date | Note
Camera Software | Mirror communication with checksum | Thibaud |  |  |  | 2017-05-10
| Validate SHWS driver V1 | Thibaud |  |  |  | 2017-05-17 | On computer and flight CPU
| Validate User Interface libraries (save data in non-volatile memory) | Thibaud |  |  |  | 2017-05-17
| Validate Image processing of SHWS images | Thibaud |  |  |  | 2017-05-17
| Validate Electrode voltages calculation | Thibaud |  |  |  | 2017-05-31
| Test Feedback loop to deform mirrors | Thibaud |  |  |  | 2017-06-08
| Test Centering/Focusing algorithm with encoders | Thibaud |  |  |  | 2017-06-15 | Need encoders
| Software | Yuchen